## 1. Team
Team Member | Role in Team | Rules | Definition of Done
Langelihle Mhlongo | Scrum Master (+Dev) | Be punctual | When the product is ready to be put into production.
Katlego Chopo | Product Owner (+Dev) | Cameras on in meetings
Ntsako Hlungwani | Dev | Do your part for the project | Product Goal
Sisanda Ndlovu | Dev | Collaborate respectfully | The goal of the invoicing system is to create an efficient and user-friendly platform that automates billing processes for tech products, ensuring accuracy and compliance with tax laws to improve customer relationships and boost overall business efficiency.
Scrum Values
Commitment
Focus
Openess
Respect
Courage

## 2. Product Vision
Front Side | Back Side
SISONKE Invoicing | An Invoicing system that provides an intuitive and user-friendly interface that enables users to create professional invoices quickly, manage client information, and track payments related to tech products. By leveraging modern technology, the system will enhance productivity, reduce manual errors, and ensure timely payments, thereby improving cash flow and customer satisfaction.
Logo: | • Customer mode - View invoices, make payment, and print invoices related to tech products
• Admin Employee mode - Manage all invoicing operations including reading, writing, editing, and removing invoices
• General Employee mode - Manage invoicing operations including reading and writing invoices
Database containing all information about the invoices:
• Customer Information
• Due Date
• Payment Status
• Simplified process to create and customize professional invoices related to tech products such as laptops, cellphones, monitor, etc. | • Can be used by anyone in the company and customers
• Track invoice statuses and payment histories in real-time. | • Requires employees and customers to be registered
• Admin Employees must create more general employee users if there is a need for more staff

## 3. Measures of Success
Features | Criteria
* Admin mode | Allow Admin to:
* Perform administrative tasks such as managing all invoices operations in high level.
* Perform administrative tasks such as reading, writing, editing and removing invoices.
* Generate Report
* Employee mode | Allow General Employee to:
* Manage employee invoices
* Reading employee Invoices.
* Writing employee Invoices.
* Create Invoices.
* Customer mode | Allow the users to:
* View Invoices.
* Make Payments.
* Secure with multiple authorisation levels | * No one can perform tasks without been logged in and authorized user.

## 4. Stakeholder Diagram
Zzimela(Admin)
Characteristics | Goals
• Access to all features and functionalities of the system. | • Efficiently manage invoicing processes
• Ability to add, edit, and delete users. | • Ensure accurate record-keeping and financial transparency
•Manage the invoicing system and its settings | •Mantain users and permission effectively
Likes | Dislikes
• Having complete control and oversight over the system. | • Complexity or unnecessary steps in performing administrative tasks.
• It values clear communication with the system | • Limited or reporting capabilities for tracking financial data
• Accessible help whenever needed | •System downtime or instability
ZackSmith (Customer)
Characteristics | Goals
• Limited access to manage their invoices and payment history. | • Access and review invoices and payment details conveniently.
• View access to relevant information about products purchased. | • Maintain a clear understanding of financial transactions
•Ability to communicate with the business regarding invoice inquiries, disputes, or clarifications. | •Receive invoices promptly
Likes | Dislikes
• Easy-to-use interface for accessing and managing invoices. | • Complicated or confusing invoice presentation or navigation.
• Transparent and accurate billing practices. | • Difficulty in resolving billing disputes or issues
•Quick and efficient payments options | • Lack of clarity or transparency in invoice details or charges.
AaronNdlovu (Employee)
Characteristics | Goals
• Limited access to certain features and functionalities based on assigned roles and permissions. | • Complete assigned tasks accurately and efficiently.
• Ability to create, manage, and send invoices to clients. | • Collaborate with colleagues and supervisors as needed.
• View access to relevant reports and analytics related to their work | •Reduce errors in invoicing
Likes | Dislikes
• User-friendly interface that makes it easy to create and manage invoices. | • Limited flexibility in performing tasks according to individual preferences.
• Clear guidelines and instructions for completing tasks within the system | • Complex systems with long chain of command
• Automation features to reduce manual work | • Lack of clarity or support in understanding system functionalities.
Invoicing System
Customers
Employees
Admins
IT Support Team
Suppliers

## 6.1. User Stories
Customer Stories
Customer
As a customer, I would like so see the customer homepage when I log on with my username and password, so that I can access the system and perform necessary tasks
As a customer, I would like to be able to submit a payment to my invoices so that I can easily manage my financial obligations and ensure timely payments.
As a customer, I would like to be able to edit my contact information, so that I can get my invoices assigned with the correct details.
As a customer, I would like to be able to view my invoices, so that I can see which invoices were paid and not paid.
As a customer, I would like to recieve a pdf format, for easy printing and offline record-keeping.
As a customer, I would like to be able to see a complete list of details about my invoices, so that I am well informed on how much I have to pay best.
As a customer, I would like to see my payment history, so that I can track my expenses, monitor my financial transactions, and maintain better control over my budgeting and accounting
As a customer, I want to the option to pay my invoice online through multiple payment methods such as credit card,bank transfer or PayPay, so that I can choose the most convenient method for me.
As a customer, I want receive notifications and reminders for upcoming and overdue invoices so that I can ensure timely payments and avoid late fees penalties.
As a customer, I would like to see my payment history, so that I can track my expenses, monitor my financial transactions, and maintain better control over my budgeting and accounting
As a customer, I want to filter and search my invoices so that I can find specific ones quickly.
Admin
As an admin, I would like to see the admin homepage when I log on with my username and password, so that I can access the system and perform administrative tasks
As an admin, I want to a manage and customize invoice templates so that our invoices reflect our company's branding and required legal information.
As an admin, I would like to generate financial reports and anallytics from the invoicing system to track our revenue and financial health accurately.
As an admin, I would like to set user permissions and access controls so that only authorized pesronnel can view or edit sensitive financial information
As an admin, I would like to be able to resolve disputes or queries raised by customers regarding thier invoices promptly and effieciently to maintain good customer relationships and trust.
As an admin, I want to automate late payment reminders to customers to reduce manual follow-up tasks and improve cash flow.
As an admin, I want to track and report on invoice aging to understand our outstanding receivables and prioritize collection efforts.
As an admin, I want offer offer and manage multiple currency invoicing to accomodate international customers and business operations.
As an admin, I want to provide customers with a breakdownof charges in their invoices to enhance transparency and trust.
As an admin, I want to monitor and audit user activity within the invoicing system to ensure compliance and identify any unauthorized access or changes.
Employee
As an employee, I would like to see the admin homepage when I log on with my username and password, so that I can access the system and perform administrative tasks
As an employee, I want to create and sent invoices to customers to ensure timely billing and cash flow.
As an employee, I want to track the status of sent invoices to know which invoices have been paid, are pending, oroverdue so that I can follow up neccesarily.
As an employee, I want to apply discounts or adjustments to invoices when needed to reflect accurate charges and maintain customer satisfaction.
As an employee, I want to record payments received against invoices in the system to keep accurate and up-to-date financial records
As an employee, I want to access customer account details, including past invoices and payment history, to provide informed and effiecient customer support.
As an employee, I want to view and manage customer payments so that I can ensure payments are recorded.
As an employee, I want to add notes to customer accounts so that important information is recorded.

## 6.2. Product Backlog
No. | Product Backlog | Category | Description
1 | As a Customer, I would like to register for an account or login securely to access the invoicing system | Customer | Starting page for the user to log into the system
2 | As an admin, I want to manage user roles and permissions to control access to sensitive financial data. | Admin | Admin page for managing users
3 | As a customer, I want to pay invoices online using multiple payment methods (credit card, bank transfer, PayPal). | Customer | Make multiple invoices payments
4 | As an admin, I want to integrate the invoicing system with our accounting software to synchronize payment data. | Admin | Integrating the invoicing system
5 | As a customer, I want to receive notifications for upcoming invoices and payment reminders. | Customer | Receiving Notifications with regards to invoices
6 | As an admin, I want to view invoices with overdue payment so that I can be able to track payments. | Admin | View Invoices with overdue payments
7 | As an admin, I want to generate financial reports and analytics to track revenue, outstanding invoices, and payment trends. | Admin | Generate Financial reports
8 | As an employee, I want to access real-time dashboard analytics to monitor invoice status and aging. | Employee | Access real time Dashboards
9 | As a customer, I want to contact support directly from the invoicing system for invoice-related queries or disputes. | Customer | Contacting support for any relelvant needed information
10 | As an admin, I want to manage and resolve customer disputes efficiently to maintain customer satisfaction. | Admin | Manage and resolve customer disputes
11 | As a customer, I want to view invoices in my preferred currency based on my location or account settings. | Customer | View Invoices
12 | As an Admin, I want to update invoice details so that customer data is accurate. | Admin | Update invoice details
13 | As an admin, I want to filter and search my invoices cycles and adjustments seamlessly. | Admin | filter and search my invoices
14 | As an employee, I want to add notes to customer accounts so that important information is recorded. | Employee | Add notes to invoices
15 | As an admin, I want to maintain an audit trail of invoice activities for compliance and security purposes. | Admin | Maintain audit trail for invoices activities
16 | As a customer, I want my invoice data to be securely stored and protected against unauthorized access. | Customer | Security on the system
17 | As a customer, I want to view and download invoices in PDF format for my records. | Customer | Get invoices in certain format
18 | As an admin, I want to customize invoice templates to reflect branding and legal requirements. | Admin | Customize invoices templates

## 7. Velocity and Sprint Backlog
No. | Product Backlog | Time Estimate | Requirement Size | Type | Priorities |  |  |  | Sprint 1 Backlog
1 | log into the system for all users | S | 2 | Functional | M | Sprint Length | 1 week | 1 | Create project Git Repository
2 | Make multiple invoices payments | M | 3 | Functional | S | Max Velocity per Sprint | 12 | 2 | Create ERD
3 | Integrating the invoicing system with rest api | L | 4 | Functional | M | Product Backlog | 48 | 3 | Create Class Diagram
4 | Receiving Notifications with regards to invoices | S | 2 | Functional | W | Total Sprints | 5 | 4 | Create EFCode1st Project
5 | View Invoices with overdue payments | S | 2 | Functional | M |  |  | 5 | Add Sample data to Pocos
6 | Generate Financial reports | M | 3 | Functional | S |  |  | 6 | Migrate EFDB To Database
7 | Access real time Dashboards | XS | 1 | Functional | C |  |  | 7 | REST API
8 | Contacting support for any relelvant needed information | XS | 1 | Functional | W | Priorities Key |  | 7.1 | Create Rest API Project
9 | Manage and resolve customer disputes | S | 2 | Functional | C | Must | M | 7.2 | Configure REST API Project and migrate Identity DB
10 | View all Invoices | S | 2 | Functional | M | Should | S | 7.3 | Migrate EFDB To REST API Project Models folder
11 | Filter and search for Invoices | M | 3 | Functional | S | Could | C | 7.4 | Create user login and registration endpoints
12 | Add notes to invoices | S | 2 | Functional | M | Want | W | 7.5 | Implement CRUD endpoints for all the entities
13 | Update invoice details | M | 4 | Functional | M |  |  | 7.6 | Test Controllers/Endpoints using In memory DB
14 | Admin page for managing users | XL | 5 | Functional | C |  |  | 7.7 | Add Log4Net for Rest API
15 | Maintain audit trail for invoices activities | L | 4 | Functional | W |  |  | 7.8 | Add XML documentation
16 | Security on the system e.g. Guards | XS | 1 | Non-Functional | M |  |  | 8 | ASP .NET
17 | Get invoices in certain format e.g pdf | L | 4 | Functional | S |  |  | 8.1 | Create ASP.NET MVC Project
18 | Customize invoices templates | M | 3 | Functional | W |  |  | 8.2 | Configure ASP.NET MVC Project
[8 empty] | 8.3 | Create Wireframe for web project
[8 empty] | 8.4 | Add Log4net
[8 empty] | 8.5 | Integrate the ASP.NET MVC invoicing system with rest api
[8 empty] | 8.5 | Add Landing page
[8 empty] | 8.6 | Add Login Page
[8 empty] | 8.7 | Add Register page
[8 empty] | 8.8 | Add authentication and authorization (AAA) of all users and reflect on pages
[8 empty] | 9 | View all Invoices
[8 empty] | 9.1 | View all Customer Invoice as Employee and Admin
[8 empty] | 9.2 | View all my Invoices as a Customer
[8 empty] | 10 | Update invoice details as an Admin
[8 empty] | 11 | Add notes to invoices
[8 empty] | 11.1 | Add notes to invoices as a Admin and Employee
[8 empty] | 12 | Make a payment as a Customer
Sprint 2 Backlog
[8 empty] | 1 | Filter and search for Invoices
[8 empty] | 2 | View Invoices with overdue payments
[8 empty] | 3 | Generate Financial reports
[8 empty] | 4 | Security on the system e.g. Guards
[8 empty] | 5 | Make multiple invoices payments
Sprint 3 Backlog
[8 empty] | 1 | Manage and resolve customer disputes
[8 empty] | 2 | Contacting support for any relelvant needed information
[8 empty] | 3 | Receiving Notifications with regards to invoices
[8 empty] | 4 | Maintain audit trail for invoices activities
5
Sprint 4 Backlog
Access real time Dashboards
[8 empty] | 1 | Optimize the system for usability
[8 empty] | 2 | Get invoices in certain format e.g pdf
[8 empty] | 3 | Customize invoices templates
4
Sprint 5 Buffer
1
2
3
4

## 8. Project Plan
|  |  | Sprint 1 |  |  | Sprint Size: | 14 | Product Goal
Product Backlog | Priorities | Requirement Size | Sprint Backlog (To do) | In Progress | Done | Impediments | Solutions | The goal of the invoicing system is to create an efficient and user-friendly platform that automates billing processes for tech products, ensuring accuracy and compliance with tax laws to improve customer relationships and boost overall business efficiency.
Access real time Dashboards | C | 1 |  |  | log into the system for all users
Manage and resolve customer disputes | C | 2 |  |  | View all Invoices
Admin page for managing users | C | 5 |  | Update invoice status
log into the system for all users | M | 2 |  | Add notes to invoices
Integrating the invoicing system with rest api | M | 4 |  |  | Integrating the invoicing system with rest api
View Invoices with overdue payments | M | 2
View all Invoices | M | 2 | Sprint 2 |  |  | Sprint Size: | 13
Add notes to invoices | M | 2 | Sprint Backlog (To do) | In Progress | Done | Impediments | Solutions
Update invoice details | M | 4 |  | Filter and search for Invoices
Security on the system e.g. Guards | M | 1 |  |  | View Invoices with overdue payments
Make multiple invoices payments | S | 3 |  | Generate Financial reports |  | Not displaying in correct format | Update CSS of the report div container
Generate Financial reports | S | 3 |  |  | Security on the system e.g. Guards
Filter and search for Invoices | S | 3 | Make multiple invoices payments |  |  | Updates payments for all users instead of specific user | Have a link that directs the selected customer to their details page
Get invoices in certain format e.g pdf | S | 4
Receiving Notifications with regards to invoices | W | 2 | Sprint 3 |  |  | Sprint Size: | 12
Contacting support for any relelvant needed information | W | 1 | Sprint Backlog (To do) | In Progress | Done | Impediments | Solutions
Maintain audit trail for invoices activities | W | 4 |  | Manage and resolve customer disputes
Customize invoices templates | W | 3 |  |  | Contacting support for any relelvant needed information
Receiving Notifications with regards to invoices
Maintain audit trail for invoices activities
|  |  | Sprint 4 |  |  | Sprint Size: | 13
|  |  | Sprint Backlog (To do) | In Progress | Done | Impediments | Solutions
Access real time Dashboards
Optimize the system for usability
Get invoices in certain format e.g pdf
|  |  | Customize invoices templates |  |  | Company logos not appearing on the customized invoice template | Check the source of the image and update image path from api

## 9. Scrum Ceremonies
Sprint Planning:
Initial Sprint Planning Meeting | Tasks | Completion Date
Sprint 0: 05/06/2024 | Assign roles | 2024-06-05
Timebox: 8h | Set working expectations | 2024-06-05
Actual time: 7h 45m | Create product vision | 2024-06-05
| Define measure of success | 2024-06-05
| Determine team velocity | 2024-06-06
| Create visioning artefacts (use case, process and UI diagrams) | 2024-06-06
| Create personas | 2024-06-06
| Define user stories | 2024-06-06
| Create the product backlog | 2024-06-06
| Create project plan | 2024-06-06
| Create definition of done | 2024-06-06
Sprint Planning Meetings | Tasks | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4
Timebox: 8h | Create sprint backlog (refer to Project Plan) | Completion Date: | Completion Date: | Completion Date: | Completion Date:
| Define order of priority for tasks | 2024-06-14 | 2024-06-21 | 2024-06-28 | 2024-07-05
| Define must, could, should, wants from tasks | Time Taken: 5h 00m | Time Taken: 3h 45m | Time Taken: 2h 30m | Time Taken: 4h 30m
| Determine type of task (functional/non-functional) | Sprint 1 Goal: | Sprint 2 Goal: | Sprint 3 Goal: | Sprint 4 Goal:
| Determine size of tasks | Create and configure EFCode1st Project, REST API, ASP .NET MVC Project. Enable user login, invoice viewing, status updating, and note addition. Integrate ASP .NET MVC invoicing system with REST API. | Implement invoice filtering and search functionality. View invoices with overdue payments. Generate financial reports. Enhance system security (e.g., guards). Enable multiple invoice payments. | Handle customer disputes efficiently. Contact support for relevant information. Receive invoice-related notifications. Maintain an audit trail of invoice activities. | Access real-time dashboards for instant insights. Optimize system usability. Obtain invoices in desired formats (e.g., PDF). Customize invoice templates for tailored branding.
Assign tasks to developers
Create sprint goal
Daily Scrums (Sprint 1):
(1) Daily Scrum Meeting(10/06) 9:00 - 9:15 | Have done (on Monday 10th) | Will do today
LLM | Created the product service. Refined product backog. Set initial business planning stage. Sprint Backlog | Create ERD
KC |  | Creating Projects on GitLab
NH | Set out measures of success and created personal and stakeholder diagram. Business Process Diagram | Pocos and Sample Data
SN | Set team norms and expectation. Updated daily scrum. Set team roles. Use Case Diagram, UI Flow Diagram | Create the REST API Project
Create the ASP .NET Project
log into the system for all users
View all Invoices
Update invoice details as an Admin
Add notes to invoices
Make a payment as a Customer
Sprint 1 Day 1 |  | Priority
Developer | Sprint Backlog (To do) |  | In Progress | Done
LLM, KC, NH, SN |  | 1 |  | Create ERD
LLM |  | 1 |  | Creating Projects on GitLab
LLM |  | 1 |  | Create the EFCode1st project
LLM |  | 1 |  | Create REST API project and add configurations
LLM |  | 2 |  | Add Test Project to REST API
LLM |  | 2 |  | Add Log4net to REST API
LLM |  | 1 |  | Add necessary NuGet packages to REST API
LLM |  | 2 |  | Create ASP.NET MVC project and add configurations
LLM |  | 2 |  | Add Test Project to ASP.NET Project
LLM |  | 2 |  | Add necessary NuGet packages to ASP.NET MVC project
KC |  | 1 |  | Notes and Invoices Pocos and Sample data
LLM |  | 1 |  | EFusers Pocos and Sample data
SN |  | 1 |  | Payments and Product Pocos and Sample data
NH |  | 1 |  | InvoiceItem and Discount Pocos and Sample data
LLM | log into the system for all users: authentication and authorization | 3
KC | View all Invoices | 3
NH | Update invoice details as an Admin | 3
KC | Add notes to invoices | 3
SN | Make a payment as a Customer | 3
(2) Daily Scrum Meeting(11/06) 9:00 - 9:15 | Have done (on Tuesday 11th) | Will do today
LLM | Create ERD | log into the system for all users in ASP.NET MVC - authentication and autherization
KC | Creating Projects on GitLab | View all Invoices
NH | Create the EFCode1st project | Update invoice details as an Admin
SN | Create REST API project and add configurations | Add notes to invoices
| Add Test Project to REST API | Make a payment as a Customer
| Add Log4net to REST API | Create Notes and Invoices Endpoints and Log them
| Add necessary NuGet packages to REST API | Create Payments and Products Endpoints and Log them
| Create ASP.NET MVC project and add configurations | InvoiceItem and Discount Endpoints and Log them
| Add Test Project to ASP.NET Project | Create Repositories (Customer-Invoices, Customer-InvoiceItem) for the Endpoints and Log them and write Repositories Tests
| Add necessary NuGet packages to ASP.NET MVC project | Create Notes and Invoices Tests
| Notes and Invoices Pocos and Sample data | Create Payments and Products Tests
| EFusers Pocos and Sample data | InvoiceItem and Discount Endpoints Tests
| Payments and Product Pocos and Sample data | Create Wireframes for front end
| InvoiceItem and Discount Pocos and Sample data | Write XML Documentation for all controllers in REST API
Sprint 1 Day 2
Developer | Sprint Backlog (To do) | Priority | In Progress | Done
LLM | log into the system for all users in ASP.NET MVC - authentication and autherization | 1
KC | View all Invoices | 3
NH | Update invoice details as an Admin | 3
KC | Add notes to invoices | 3
SN | Make a payment as a Customer | 3
KC |  | 1 |  | Create Notes and Invoices Endpoints and Log them
SN |  | 1 |  | Create Payments and Products Endpoints and Log them
NH |  | 1 |  | InvoiceItem and Discount Endpoints and Log them
LLM |  | 2 | Create Repositories (Customer-Invoices, Customer-InvoiceItem) for the Endpoints and Log them
KC |  | 3 | Create Notes and Invoices Tests
SN |  | 3 | Create Payments and Products Tests
NH |  | 3 | InvoiceItem and Discount Endpoints Tests
LLM |  | 3 | Repositories Tests
LLM, KC, NH, SN |  | 2 |  | Write XML Documentation for all controllers in REST API
LLM |  | 2 |  | Create Wireframes - Login and Register pages
KC |  | 2 |  | Create Wireframes - Customers home page, customers invoices page including invoice details page
NH |  | 2 |  | Create Wireframes - Admin home page and landing page
SN |  | 2 |  | Create Wireframes - Employee home, products, invoices, and profile pages
(3) Daily Scrum Meeting(12/06) 9:05 - 9:15 | Have done (on Wednesday 12th) | Will do today
LLM | Create Notes and Invoices Endpoints and Log them | View all Invoices
KC | Create Payments and Products Endpoints and Log them | Update invoice details as an Admin
NH | InvoiceItem and Discount Endpoints and Log them | Add notes to invoices
SN | Write XML Documentation for all controllers in REST API | Make a payment as a Customer
| Create Wireframes - Login and Register pages | Create CustomerInvoices Repository for the Endpoints and Log them
| Create Wireframes - Customers home page, customers invoices page including invoice details page | Create Notes and Invoices Tests
| Create Wireframes - Admin home page and landing page | Create Payments and Products Tests
| Create Wireframes - Employee home, products, invoices, and profile pages | InvoiceItem and Discount Endpoints Tests
CustomerInvoices Repository Tests
Create Customers private pages
Create Admins private pages
Create Employee private pages
log into the system for all users in ASP.NET MVC - authentication and autherization
Create Landing page
Sprint 1 Day 3
Developer | Sprint Backlog (To do) | Priority | In Progress | Done
KC | View all Invoices | 3
NH | Update invoice details as an Admin | 3
KC | Add notes to invoices | 3
KC | Make a payment as a Customer | 3
LLM |  | 1 |  | log into the system for all users in ASP.NET MVC - authentication and autherization
LLM |  | 3 |  | Create CustomerInvoices Repository for the Endpoints and Log them
KC | Create Notes and Invoices Tests | 2
SN, LLM |  | 2 |  | Create Payments and Products Tests
NH | InvoiceItem and Discount Endpoints Tests | 2
LLM |  | 2 |  | CustomerInvoices Repository Tests
KC |  | 1 |  | Create Customers home pages
NH |  | 1 |  | Create Admins home pages
SN |  | 1 |  | Create Employee home pages
LLM |  | 1 |  | Create Landing page
(4) Daily Scrum Meeting(13/06) 9:05 - 9:15 | Have done (on Thursday 13th) | Will do today
LLM | log into the system for all users in ASP.NET MVC - authentication and autherization | View all Invoices
KC | Create CustomerInvoices Repository for the Endpoints and Log them | Update invoice details as an Admin
NH |  | Add notes to invoices
SN | Create Payments and Products Tests | Make a payment as a Customer
Create Notes and Invoices Tests
| CustomerInvoices Repository Tests | InvoiceItem and Discount Endpoints and Tests
| Create Customers home pages | Customer Payments Repo REST API
| Create Admins home pages | Customer Payments page ASP.NET MVC
| Create Employee home pages | Customer InvoiceItems Repo
| Create Landing page | Customer Invoice Details page
Customer, Admin, Employee Profile pages
Design Patterns Rest API
Create ASP.NET MVC Controller Tests
Log Invoice and Notes controllers in both REST API and MVC APP
Log Payments and Products controllers in both REST API and MVC APP
Log Discounts and InvoiceItems controllers in both REST API and MVC APP
Sprint 1 Day 4
Developer | Sprint Backlog (To do) |  | In Progress | Done
KC |  |  |  | View all Invoices
NH |  |  | Update invoice details as an Admin
KC |  |  | Add notes to invoices
KC |  |  |  | Make a payment as a Customer
KC |  |  |  | Create Notes and Invoices Tests
NH |  |  | InvoiceItem and Discount Endpoints Tests
KC |  |  |  | Customer Payments Repo REST API
KC |  |  |  | Customer Payments page ASP.NET MVC
LLM |  |  |  | Customer Invoice Details page
KC |  |  |  | Customer, Admin, Employee Profile pages
LLM |  |  |  | Customer, Admin, Employee Profile pages
NH |  |  | Create Discounts Tests
LLM |  |  |  | Create ASP.NET MVC Controller Tests
KC |  |  |  | Log Invoice and Notes controllers in both REST API and MVC APP
SN |  |  |  | Log Payments and Products controllers in both REST API and MVC APP
NH |  |  | Log Discounts and InvoiceItems controllers in both REST API and MVC APP
LLM |  |  |  | Design Patterns on REST API (Singleton, Factory, and Strategy)
Sprint Review:
Sprint Review Meeting (14/06/2024) | Feedback
Timebox: 4h | Recieved very positive feedback overall
Actual time: 2h 30m | High praise on the user stories and personas
Attendees: | Stakeholders were very happy with the overall functionality
Product Owner - KC | No change was made to the process diagram
Scrum Master - LLM
Developers - LLM,KC,NH,SN
Stakeholders
Sprint Retrospective:
Sprint Retrospective 1 | Positives
Date Completed:14/06/2024 | The team collaborated effectively, ensuring that all assigned tasks were completed promptly.
Timebox: 2h | Each member showed dedication and responsibility, contributing to the project's success.
Actual time: 1h 58m | We discussed each member's responsibilities to ensure everyone understood their roles, leading to a successful project.
The invoicing system infrastructure was successfully set up, including databases and server configurations.
Future Improvements
The conversation time could be cut back to enable higher productivity.
We need to work on providing more accurate time estimates for tasks to better manage our workload and avoid overcommitting.
Sprint Retrospective 2 | Positives
Date Completed: 21/06/2024 | We managed to cut back on conversation and improve productivity.
Timebox: 2h | The user interface was refined to be more user-friendly.
Actual time: 1h | Through regular progress updates, we've fostered a culture of transparency and accountability
We have successfully improved our capability to provide precise time estimates for tasks, allowing us to effectively manage.
Future Improvements
Implementing more efficient communication tools can ensure seamless information exchange among team members
Sprint Retrospective 3 | Positives
Date Completed: 28/06/2024 | Core functionalities such as invoice creation, storage, and retrieval were implemented.
Timebox: 2h | The team communicated effectively and collaborated well.
Actual time: 1h 58m | The efficiency of the team has improved a lot since the first sprint and we have made great progress.
Quick identification and resolution of bugs from the previous sprint.
Future Improvements
None, eveything is clear as a group
Sprint Retrospective 4 | Positives
Date Completed: 05/07/2024 | The product works across different platforms and we resolved issues of response time.
Timebox: 2h | The team came together really well to create a finalised product.
Actual time: 1h 45m | Added features like invoice editing and deletion based on user feedback.
Future Improvements
We have worked very well and completed the project.

## 10. Burndown
| Start | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5
Ideal Velocity | 12 | 12 | 12 | 12 | 12 | 12 | Day | Points remaining | Day | Points remaining | Day | Points remaining | Day | Points remaining | Day | Points remaining
Actual Velocity |  | 14 | 9 | 12 | 9 | 4 | 1 | 12 | 1 | 12 | 1 | 12 | 1 | 12 | 1 | 12
Remaining | 48 | 34 | 25 | 13 | 4 | 0 | 2 | 10 | 2 | 9 | 2 | 9 | 2 | 11 | 2 | 8
Projected | 48 | 36 | 24 | 12 | 0 | 0 | 3 | 8 | 3 | 7 | 3 | 7 | 3 | 6 | 3 | 8
[7 empty] | 4 | 2 | 4 | 4 | 4 | 3 | 4 | 3 | 4 | 8
[7 empty] | 5 | 0 | 5 | 3 | 5 | 0 | 5 | 3 | 5 | 8

## 16. Sample Data for User Reg
Sample Data
{ "userName": "HaalandS2Admin", "email": "HaalandS@gmail.com", "address": "43 Big Street, 4302", "phoneNumber": "0743929000", "password": "Haaland@1234", "firstName": "Sergio", "lastName": "Haaland", "role": "Administrator" }
{ "userName": "JackG", "email": "Jackg@gmail.com", "address": "45 Manchester Road, 4367", "phoneNumber": "0749323223", "password": "JackG@123456", "firstName": "Jack", "lastName": "Grealish", "role": "Employee" }
{ "userName": "Havertz02", "email": "Harvertzj@gmail.com", "address": "43 Arsenal Road, 3453", "phoneNumber": "0743232223", "password": "Harvetz@1234", "firstName": "Julian", "lastName": "Harvetz", "role": "Customer" }

## 17. Sample Data for User Login
| Username | Password | Role
Customer | Efronz | Efron@123456 | Customer
Employee | Jkhalid | Khalidj@1234 | Employee
Administrator | ZzimelaAdmin | zimelaZ@1234 | Administrator

## 18. Design Pattern
logging framework
Name of Framework | log4net
Name (and path) of log file | SISONKE_Invoicing_System_RestAPIRolling, located in the bin folder of the project
Design Patterns
Name of Design Patterns | Strategy Pattern, Factory Pattern, and Singleton
Where/how it's used | In the REST API application. The strategy design pattern is used for checking the user role. The factory design pattern is used for sending the appropriate response message whether ok, bad, or not found response. The singleton is used through the log4net instance, one is created and is used across the system. It requires the name of the controller to keep track of where it is called